## Change-Defect_Lookups
Status |  | Type
Proposed |  | Change
Approved |  | Defect
Denied
<- Add more or change status options
<- Add more or change status options

## Change_Defect_Log
# | Submitted | Requested By | Type | Description | Scope Impact | Timeline Impact | Budget Impact | Status | Date Resolved | New Budget
|  |  |  | Original Budget | [5 empty] | 30000
1 | 2009-01-01 | John Doe | Change | New Product Feature |  | Extend development until 3/2/2009 | 30000 | Approved | 2009-02-01 | 60000 | 3
2 | 2009-04-01 | John Doe | Defect | Purchase second server |  | no impact to schedule our resources | 12000 | Denied | 2009-02-15 | 60000 | 1
3 | 2009-05-01 | John Doe | Defect | Provide end-user documentation |  | Extend deployment | 6000 | Proposed | 2009-03-02 | 60000 | 2
4 | 2009-06-22 | John Doe | Change | Bring in external consultant |  | Speed development | 5000 | Approved | 2009-07-03 | 65000 | 3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on J2: Generally, all defects should be approved.

## Change_Defect_Dashboard
Count Breakdown | Change | Defect | Total
Proposed | 0 | 1 | 1
Approved | 1 | 0 | 1
Denied | 0 | 0 | 0
Total | 1 | 1 | 2