## Project_Plan
Navigate Project Plan Template
[Enter Project Here]
[Enter Date Here]
WBS | Activities (associate deliverabes in column D) | Deliverables | Owner | Status | Start | Finish | Work (days) | % | time axis 2022-01-02 to 2023-01-01
0 | [Enter Project Here] |  |  |  | 0 | 0 | 0 | 0%
1 | Assemble & Define |  |  |  | 0 | 0 | 0 | 0%
1.1 | Build Business Case | Business Case |  | Scheduled |  |  |  | 0%
1.2 | Build Team | Project Charter, Team Organization Chart, Contact List, Roles & Responsibilities |  | Scheduled |  |  |  | 0%
1.3 | Determine Project Mgmt Approach | Approval & Prioritization, Project Management Plan |  | Scheduled |  |  |  | 0%
1.4 | Establish Requirements | Requirements Definition Framework |  | Scheduled |  |  |  | 0%
1.5 | Prepare Collaboration Site | Collaboration Mgmt Site |  | Scheduled |  |  |  | 0%
2 | Evaluate & Decide |  |  |  | 0 | 0 | 0 | 0%
2.1 | Coordinate Bid Process | Request for Information, Request for Proposal |  | Scheduled |  |  |  | 0%
2.2 | Drive Decision-Making Process | Decision Scorecard |  | Scheduled |  |  |  | 0%
2.3 | Negotiate Legal Contracts | Contracts |  | Scheduled |  |  |  | 0%
2.4 | Determine ROI | 5 Year NPV Estimate |  | Scheduled |  |  |  | 0%
2.5 | Facilitate Gate Review #1 | All Deliverables from Stage 1 & 2 |  | Scheduled |  |  |  | 0%
3 | Plan & Learn |  |  |  | 0 | 0 | 0 | 0%
3.1 | Mobilize Project Team | Resource Plan |  | Scheduled |  |  |  | 0%
3.2 | Kickoff Project Implementation | Kickoff Presentation |  | Scheduled |  |  |  | 0%
3.3 | Build Project Outlook | Milestone Schedule/Timeline, Project Plan & Scorecard |  | Scheduled |  |  |  | 0%
3.4 | Establish Project Mgmt Tools | Communication Plan & Scorecard, Budget Tracker & Scorecard, Change/Defect Tracker & Scorecard, Issue/Risk Tracker & Scorecard |  | Scheduled |  |  |  | 0%
3.3 | Train Core Team | Core Team Training Plan & Scorecard |  | Scheduled |  |  |  | 0%
4 | Analyze & Design |  |  |  | 0 | 0 | 0 | 0%
4.1 | Facilitate Design Workshops | Process Design Flow Charts |  | Scheduled |  |  |  | 0%
4.2 | Address Requirement Gaps | Development List & Scorecard, Development Design Specifications |  | Scheduled |  |  |  | 0%
4.3 | Document Design Decisions | Process Design Specifications, Security Plan & Scorecard |  | Scheduled |  |  |  | 0%
4.4 | Determine System Landscape | System Infrastructure Diagram, System Environment Plan |  | Scheduled |  |  |  | 0%
4.5 | Build Test Approach | Test Plan & Scorecard |  | Scheduled |  |  |  | 0%
4.6 | Facilitate Gate Review #2 | All Deliverables from Stage 3 & 4 |  | Scheduled |  |  |  | 0%
5 | Configure & Build |  |  |  | 0 | 0 | 0 | 0%
5.1 | Perform & Document Installations | Installation & Environment Specifications |  | Scheduled |  |  |  | 0%
5.2 | Perform & Document Configurations | Configuration Specifications |  | Scheduled |  |  |  | 0%
5.3 | Perform & Document Codings | Development Technical Specifications |  | Scheduled |  |  |  | 0%
5.4 | Build Test Scripts | Test Scipts, Test Data Set |  | Scheduled |  |  |  | 0%
6 | Test & Resolve |  |  |  | 0 | 0 | 0 | 0%
6.1 | Load Test Data Set | Test environment |  | Scheduled |  |  |  | 0%
6.2 | Execute Test Plan, Cycles, & Scripts | Completed Test Scripts |  | Scheduled |  |  |  | 0%
6.3 | Track & Resolve Changes/Defects | Change/Defect Tracker & Scorecard, Issue/Risk Tracker & Scorecard |  | Scheduled |  |  |  | 0%
6.4 | Build End User Training Approach | End User Training Plan & Scorecard, Training Data Set |  | Scheduled |  |  |  | 0%
6.5 | Build End User Training Material | End user Training Schedule and Content |  | Scheduled |  |  |  | 0%
7 | Prepare & Learn |  |  |  | 0 | 0 | 0 | 0%
7.1 | Load Training Data Set | Training environment |  | Scheduled |  |  |  | 0%
7.2 | Deliver Training | End User Training Plan & Scorecard |  | Scheduled |  |  |  | 0%
7.3 | Build Cut-over Approach | Cut-Over Plan & Scorecard |  | Scheduled |  |  |  | 0%
7.4 | Perform Go-Live Readiness Evaluation | Go-Live Readiness Assessment |  | Scheduled |  |  |  | 0%
7.5 | Prepare Support Teams & Processes | Support Transfer Plan |  | Scheduled |  |  |  | 0%
7.6 | Facilitate Gate Review #3 | All Deliverables from Stage 5 & 6 & 7 |  | Scheduled |  |  |  | 0%
8 | Deploy & Support |  |  |  | 0 | 0 | 0 | 0%
8.1 | Conduct Feedback Survey | Post-Implementation Survey |  | Scheduled |  |  |  | 0%
8.2 | Facilitate Lessons Learned Workshop | Lessons Learned Log |  | Scheduled |  |  |  | 0%
8.3 | Stabilize Project Deployment Impact | Post Go-Live Support |  | Scheduled |  |  |  | 0%
8.4 | Determine Outcome Realization | Outcome Realization Scorecard |  | Scheduled |  |  |  | 0%
8.5 | Facilitate Gate Review #4 | All Deliverables from Stage 8 |  | Scheduled |  |  |  | 0%