## Instructions
General Instructions
1.) Review and set/update the estimate parameters assigned for each intersection of solution classification and project phase in the 'Estimate_Factors' tab.
2.) Review and set/update the number of expected working hours in a day for the associated project on the 'Estimate_Factors' tab.
3.) Review and set/update the 'Effort_Splits' tab. This tab is intended to identify how much of each estimate by phase should be allocated across the various resource types.
4.) Log all custom solutions on the 'Solution_Definition' tab. Be sure to complete columns B,C,D,E, & F for each row that is entered. Columns D,E,&F are critical for the related estimates to be automatically generated.
5.) Review the 'Summary' tab for a basic summary analysis of solution counts & effort estimates.

## Estimate_Factors
Estimate Factors - Custom Solutions
Number Of Hours in a Working Day | 8
Number Of Days in a Working Week | 5
Solution Classifications
| Reports |  |  | Interfaces |  |  | Conversions |  |  | Enhancements
Project Phase | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High
Lookup Value | RL | RM | RH | IL | IM | IH | CL | CM | CH | EL | EM | EH
Rqmts | 1 | 2 | 4 | 2 | 4 | 6 | 2 | 4 | 6 | 2 | 3 | 5
Design | 2 | 4 | 6 | 8 | 12 | 16 | 8 | 12 | 16 | 3 | 5 | 8
Construct | 2 | 4 | 6 | 8 | 16 | 32 | 8 | 16 | 32 | 5 | 10 | 15
Test | 1 | 2 | 3 | 2 | 4 | 6 | 2 | 4 | 6 | 3 | 5 | 8
Rework | 1.5 | 3 | 4.75 | 5 | 9 | 15 | 5 | 9 | 15 | 3.25 | 5.75 | 9
Total Effort- HOURS: | 7.5 | 15 | 23.75 | 25 | 45 | 75 | 25 | 45 | 75 | 16.25 | 28.75 | 45
Number of Weeks For Rqmts Phase | bar: RL
Number of Weeks For Design Phase | RL: 4
Number of Weeks For Build Phase | RL: 5
Number of Weeks For Test Phase | RL: 3; RM: NOTE: Test & Rework # of Weeks Must Sum tto Total # of Weeks in Test Phase.
Number of Weeks For Rework Phase | RL: 3
Number of Weeks For Project SDLC | RL: 16; RM: NOTE: Auto-calculated

## Effort_Splits
Estimate Distributions Across Resource Type
Resource Type | Rqmts | Design | Construct | Test | Rework
BUSINESS ANALYST | 100% | 75% | 0% | 90% | 25%
DEVELOPER | 0% | 25% | 100% | 10% | 75%
TOTALS | 100% | 100% | 100% | 100% | 100%
**NOTE: Each Column needs to sum to 100%.

## Solution_Definition
SDLC Solution Estimates
|  |  |  | ESTIMATE DRIVERS |  |  | RQMTS |  |  | DESIGN |  |  | CONSTRUCT |  |  | TEST |  |  | REWORK |  |  | TOTAL SOLUTION EFFORT
Solution ID | Solution Name | Solution Description (including Source -> Target data flows for each import & export for conversions and interfaces) | Development Team | Solution Type: (R,I,C,E) | Complexity: (L - Low, M - Med, H - High) | Leverage %: (0 to 100%) | Total | BUSINESS ANALYST | DEVELOPER | Total | BUSINESS ANALYST | DEVELOPER | Total | BUSINESS ANALYST | DEVELOPER | Total | BUSINESS ANALYST | DEVELOPER | Total | BUSINESS ANALYST | DEVELOPER | TOTAL | BUSINESS ANALYST | DEVELOPER
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Copy this line and insert directly above to add more rows to the spreadsheet… | [5 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD1 | HOURS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD1 | DAYS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD1 | SINGLE FTE WEEKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD1 | FTEs NEEDED TO MEET SCHEDULE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD2 | HOURS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD2 | DAYS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD2 | SINGLE FTE WEEKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD2 | FTEs NEEDED TO MEET SCHEDULE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD3 | HOURS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD3 | DAYS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD3 | SINGLE FTE WEEKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TBD3 | FTEs NEEDED TO MEET SCHEDULE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | HOURS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | DAYS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | SINGLE FTE WEEKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | FTEs NEEDED TO MEET SCHEDULE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary
DASHBOARD
Object Type | Complexity | Count
Reports | Total | 0
| H | 0
| M | 0
| L | 0
Interfaces | Total | 0
| H | 0
| M | 0
| L | 0
Conversions | Total | 0
| H | 0
| M | 0
| L | 0
Enhancements | Total | 0
| H | 0
| M | 0
| L | 0
TOTAL |  | 0
Solution Type | % of Total
Reports | #DIV/0!
Interfaces | #DIV/0!
Conversions | #DIV/0!
Enhancements | #DIV/0!
Estimates by Solution Type
Solution Type | Days | Hours
Reports | 0 | 0
Interfaces | 0 | 0
Conversions | 0 | 0
Enhancements | 0 | 0
TOTAL | 0 | 0
Estimates by Resource Type
Resource Type | Days | Hours
BUSINESS ANALYST | 0 | 0
DEVELOPER | 0 | 0
TOTAL | 0 | 0
Estimates by Project Phase - TOTAL
Phase | Days | Hours
Rqmts | 0 | 0
Design | 0 | 0
Construct | 0 | 0
Test | 0 | 0
Rework | 0 | 0
TOTAL | 0 | 0
Estimates by Project Phase -BUSINESS ANALYST
Phase | Days | Hours
Rqmts | 0 | 0
Design | 0 | 0
Construct | 0 | 0
Test | 0 | 0
Rework | 0 | 0
TOTAL | 0 | 0
Estimates by Project Phase - DEVELOPER
Phase | Days | Hours
Rqmts | 0 | 0
Design | 0 | 0
Construct | 0 | 0
Test | 0 | 0
Rework | 0 | 0
TOTAL | 0 | 0